## Gantt Chart
Gantt Chart – 2-Player Shooting Game Toy ¦ 14 Weeks
WBS ID | Task / Work Package | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
[9 empty] | BREAK |  | ★ MS
1 | Full Game | W8: ////; W10: ★
1.1 | Project Management
1.2 | User Research & Design Thinking
1.3 | Product Design Specification (PDS)
1.4 | Mechanical Subsystems | W8: ////
1.4.1 | Shooting Mechanism
1.4.1.1 | Research shooting methods | bar: W2 to W4; W10
1.4.1.2 | CAD model (Autodesk Inventor) ★
1.4.1.3 | Projectile calculations ★ | bar: W3 to W6; W10
1.4.1.4 | Material selection | bar: W1 to W5; W7; W9 to W14
1.4.1.5 | Manufacturing & assembly | bar: W6 to W7; W10
1.4.2 | Vertical Lifting Mechanism
1.4.2.1 | Mechanism research | bar: W2 to W4; W10
1.4.2.2 | CAD model ★
1.4.2.3 | Load / torque calculations ★ | bar: W5 to W7; W10
1.4.2.4 | Actuator selection & sizing ★
1.4.2.5 | Manufacturing & assembly | W8: ////
1.4.3 | Sorting Mechanism
1.4.3.1 | Sorting method selection | bar: W2 to W3; W10
1.4.3.2 | CAD model ★ | bar: W1 to W4; W7; W9 to W14
1.4.3.3 | Sensor selection | bar: W4; W10
1.4.3.4 | Manufacturing & assembly | W8: ////; W10: ★
1.5 | Electrical & Electronics System
1.5.1 | Component selection
1.5.2 | Circuit design (Proteus) | bar: W7; W9 to W10
1.5.3 | PCB design & fabrication ★ | bar: W1 to W7; W10 to W14
1.5.4 | Wiring diagrams (each subsystem) ★ | W8: ////; W10: ★
1.6 | Embedded Systems & Software | W8: ////; W10: ★
1.7 | System Integration | bar: W9 to W12
1.7.1 | Mechanical integration | bar: W1 to W7; W9 to W14
1.7.2 | Electrical integration | bar: W9 to W10
1.7.3 | Wiring and connections | bar: W1 to W7; W9 to W14
1.9 | Testing & Validation
1.9.1 | Subsystem testing | bar: W1 to W7; W9 to W14
1.9.2 | Electrical testing | bar: W9 to W11
1.9.3 | Software testing
1.9.4 | Integrated system testing | bar: W10 to W12
1.10 | Finalization
1.10.1 | Final wiring | bar: W10; W12 to W13
1.10.2 | Final code debugging
1.10.3 | Theme & aesthetics completion | bar: W10; W13
1.10.4 | Final layout
1.11 | Documentation & Deliverables
1.11.2 | Presentation slides
1.11.3 | A0 poster | bar: W10; W12 to W14
1.11.4 | Video demonstration
1.11.5 | Bill of Materials (BOM) | bar: W9 to W12
1.11.6 | Flowcharts & block diagrams ★ | W8: ////
1.11.7 | GitHub repository organization | bar: W3 to W7; W9 to W14
1.11.8 | WBS ★