## WBS
Work Breakdown Structure – 2-Player Shooting Game Toy
WBS ID | Task / Work Package
1 | Full Game
1.1 | Project Management
1.1.1 | Task planning & role distribution
1.1.2 | Gantt chart creation
1.2 | User Research & Design Thinking
1.2.1 | Identify user needs & problems
1.2.2 | Ideation (mind maps, sketches)
1.2.3 | Concept selection
1.3 | Product Design Specification (PDS)
1.3.1 | Functional requirements
1.3.2 | Safety requirements
1.3.3 | Size and constraints
1.3.4 | Performance criteria
1.4 | Mechanical Subsystems
1.4.1 | Shooting Mechanism
1.4.1.1 | Research shooting methods
1.4.1.2 | CAD model (Autodesk Inventor)
1.4.1.3 | Projectile calculations ★
1.4.1.4 | Material selection
1.4.1.5 | Manufacturing & assembly
1.4.2 | Vertical Lifting Mechanism
1.4.2.1 | Mechanism research
1.4.2.2 | CAD model
1.4.2.3 | Load / torque calculations ★
1.4.2.4 | Actuator selection & sizing ★
1.4.2.5 | Manufacturing & assembly
1.4.3 | Sorting Mechanism
1.4.3.1 | Sorting method selection
1.4.3.2 | CAD model ★
1.4.3.3 | Sensor selection
1.4.3.4 | Manufacturing & assembly
1.5 | Electrical & Electronics System
1.5.1 | Component selection
1.5.2 | Circuit design (Proteus)
1.5.3 | PCB design & fabrication ★
1.5.4 | Wiring diagrams (each subsystem) ★
1.6 | Embedded Systems & Software (Game Software)
1.7 | System Integration
1.7.1 | Mechanical integration
1.7.2 | Electrical integration
1.7.3 | Wiring and connections
1.8 | Testing & Validation
1.8.1 | Subsystem testing
1.8.2 | Electrical testing
1.8.3 | Software testing
1.8.4 | Integrated system testing
1.9 | Finalization
1.9.1 | Final wiring
1.9.2 | Final code debugging
1.9.3 | Theme & aesthetics completion
1.9.4 | Final layout
1.10. | Documentation & Deliverables
1.10.1 | Presentation slides
1.10.2 | A0 poster
1.10.3 | Video demonstration
1.10.4 | Bill of Materials (BOM)
1.10.5 | Flowcharts & block diagrams ★
1.10.6 | GitHub repository organization
1.10.7 | WBS ★

## Legend & Guide
COLOUR LEGEND
Level 1 – Project (dark navy) | Top-level project node
Level 2 – Major phases (blue) | e.g. 1.1 Project Management
Level 3 – Sub-phases (mid blue) | e.g. 1.4.1 Shooting Mechanism
Level 4 – Work packages (light blue) | Individual tasks with owners
MILESTONE ITEMS (★) | Items marked ★ are required for the Week 10 milestone check
1. Integrated CAD Design | All subsystem CAD models complete
2. Functional Subsystems | Each subsystem independently operational
3. Actuator Sizing | All actuators sized with calculations
4. Projectile Calculations | Range, velocity, force calculations
5. WBS | This document
6. Gantt Chart | 14-week schedule
7. PDS | Product Design Specifications
8. System Flowchart | Whole system flowchart
9. System Block Diagram | Whole system block diagram
10. Wiring Diagrams & PCB Schematic | At least one complete PCB schematic
STATUS OPTIONS | Edit column H on the WBS sheet
Not started
In progress
Complete
On hold
At risk